## Slide 1: Planning, Selling, and Executing a Project
Community Service Committee

## Slide 2: Process
Set up teem
Gather information
Plan project
Meat with department
Present to other departments

## Slide 3: Set up team
Responsibilities
  Contact people recommended as department reps
  Pursue leads until all positions are filled
  Get CSCom buyoff

## Slide 4: Gather information
Questions for team leaders
  How much time do you want/have available to spend?
  How much time do you want your team to spend?
  Do you have a project you have always wanted to do?
  Is there a project you are already doing (or already plan to do) that we can help with?
  How much do you want the team to be involved in choosing the the project?
Notes: If audience members bring up other topics that seem to fit the discussion, add those here.

## Slide 5: Gather information (continued)
Questions for department reps
  What kinds of things are your employees interested in?
  What is the skill level of your employees?
  What is the commitment level of your employees?
  What type of project do you see as being successful for these employees (collection, activity, fundraising; see Resource notebook)?
  Can you recommend an employee who would be a good community service planner for your department?

## Slide 6: Plan project
When will the project begin and end?
When will the project be introduced to the employees?
How much input will the employees have in the choice of the project?
What tasks will be involved in carrying out the project?
Who will do those tasks?

## Slide 7: Meet with department
Introduce the project to the employees
  Writing about experiences
  Listing ideas about populations in need
  Reading articles or inspirational stories (Médecins Sans Frontières)
Outline the parameters of the project
  Timeline
  How much department time is involved?
  Project participation extended to all employees

## Slide 8: Meet with department (continued)
Lead discussion
  What kind of project do we want to do?
  What need do we want to address?
  What are the goals of this project?
  What do we need to do to meet those goals?
  Who will perform these tasks?
  What materials will we need?
  When will the tasks be performed?

## Slide 9: Present to other departments
Consult with team leader about the best way to communicate
Team leader may bring up at next team leaders’ meeting
Method will depend on the project and the decisions made in the department meeting